## Nov 2025
9/12/2025 -- Done since September | Status | Staff | Notes
Incident Recovery Tabletop Exercise | Done | Pete | First dry run went well, but showed a need for continued refreshers
Add Montello yearbooks to ResCarta | Done | Keetra
Networking, PC support, and email
Adding Bandwidth Router Licenses | In Process | Pete/Jay | Badgernet is moving all 50M locations to 100M, licenses added, NK, PK, OX, EN and PS done. C-Port, PineR, MillPond, Montello, Prince pending
Shift Shared Files into SharePoint | In Process | All | moving WALS file share into SharePoint
Researching new backup software | In Process | Pete | Replacement for collaborative Avamar system
Migrating ESET to cloud server | In Process, ongoing | Pete | Some laptop stragglers. 95% migrated
New Host Server | In Process | Pete/Jay/Karla/MK | Host server ready: SD VMs will get set up next
Online catalog
Symphony and WorkFlows
Testing new reports and services from SD | In Process | Karla, Melissa | Customized Cardswipe/OnlinePay report; improved online renewal process
New Sticky Receipt printers | In Process | Melissa | 3 new printers on order for NPL, 2 for Berlin. OPL's are working with Win11, so on hold until 2026 for budgetary reasons.
Testing new Symphony 4.2 upgrade | In Process | Melissa, Karla | Some major new features including the ability to have non-transitable items and share ownership of WF reports so that libraries no longer need to login as REPORTS.
Testing new APP | On Hold | Karla, Melissa | SD is working on getting Linked Cards out by the end of the year. Due to the SD purchase, all timelines and product development schedules have been re-arranged.
Piloting New BC Acquisition software | On Hold | Melissa, Crystal | SD has paused development on BC Acq to focus on BC Circ. We are waiting on one, very small, bug fix so that Crystal can streamline the invoicing procedures that might still happen soon.
Improve volume handling in catalog and WF | On hold | Karla, Melissa | Got shoved aside by Problem Items and other things.
Website development and support
Mass migrate or rebuild sites before software EOL | In Process | Jay | All of the Drupal 7 sites (15) need to be updated. Update 4/28/25: Only two library sites remain. Update 9/8/25 One site remains.
Upgrade Drupal 9 sites to Drupal 10 | In Process | Jay | Drupal 9 sites need to be updated to Drupal 10. Like the upgrade from 8 to 9, the switch from 9 to 10 is a major version update and brings with it some significant user interface changes.
Hancock Public Library website | In Process | Jay | One of the remaining sites left on Drupal 7.
Research DB API and Plugin (Drupal version) | On Hold | Jay | Update 7/1/2025: It looks more realistic that all library websites will be on a new platform before the plugin can be ported to Drupal.
Digitization/Indexing
"Bagging" & Uploading backup of ResCarta data to the state | In Process | Keetra | Participating in the statewide Digital Achive Backup project because it never hurts to have multiple backups!
Creating a ResCarta inventory | Near Done | Keetra | This was moved up the priority list because of our participation in the statewide Digital Archive Backup project.
Mitigate all possible ResCarta security concerns | In Process, ongoing | Keetra, Pete | Currently working on spinning up a replacement for the server with newer versions of the software.
Add Fond du Lac images to ResCarta | In Process | Keetra | Restructured directory of images to prepare for import.
Add Westfield yearbooks to ResCarta | In Process | Keetra
Add Berlin newspapers to ResCarta. | Upcoming | Keetra | Berlin is reviewing images received from Crowley.
Investigate interest in combined Cemetery index similar to Vital Records index | On Hold | Keetra | An email was sent out to directors inquiring whether their library had any paper or electronic records. Few libraries replied.
Investigate adding Wild Rose local history audio files to ResCarta | Upcoming | Keetra | This will be the first audio to be added.
Investigating collaboration with other library ResCarta sites in Wisconsin | Upcoming | Keetra
Other
Cleanup Overdrive Marketplace Accounts / Overdrive Support email configuration | Near Done | Keetra, Pete | Many accounts were out of date due to staff turnover, a number of email addresses were defunct. Waiting to hear back from a handful of libraries.