## Jan 2026
3/13.2026 -- Done since November 2025 | Status | Staff | Notes
New Sticky Receipt printers | SemiDone | Karla | Neenah, Berlin Done. OPL's ordered
Hancock Public Library website | Done | Jay | One of the remaining sites left on Drupal 7.
Mass migrate or rebuild sites before software EOL | Done | Jay | As of 2/18/26 all library sites on Drupal 7 have been replaced.
Research DB API and Plugin (Drupal version) | Discarded | Jay | Update 2/27/2026: The remaining library sites (5) on Drupal will be replaced in 2027.
Migrating ESET to cloud server | Done | Pete
Researching new backup software | Done | Pete | Unitrends up and running
New Host Server | Done | Pete/Jay | VMs migrated from old Host to new
Networking, PC support, and email
Adding Bandwidth Router Licenses | In Process | Pete/Jay | Badgernet is moving all 50M locations to 100M, licenses added, NES, PAC, OXF, END, POY, PIN done. CAM, KIN, MON, PRI pending
Shift Shared Files into SharePoint | In Process | All | file naming stds set, more depts working on it
New Core Switch | In Process, ongoing | Pete/Jay | Switch ordered
Fond du Lac Public M365 Integration | In Process | Pete/Jay | domain added, test account created
EOL Servers Upgraded | In Process | Pete/Keetra | EZProxy, Papercut and ER servers need to migrate to latest OS
Meraki wifi AP updates | In Process | Pete | 17 new APs to be deployed
Crisis Exercise | Pending | Pete - All | new incident response training exercise
Online catalog
Symphony and WorkFlows
Testing new Symphony 4.2 upgrade | In Process | Karla, Annie | Some major new features including the ability to have non-transitable items and share ownership of WF reports so that libraries no longer need to login as REPORTS.
Renew SD contract | Upcoming | Karla | Our 7-year contract ends at the end of this year. Currently SD isn't offering as long contracts or as good deals, so we'll see.
Testing new APP | On Hold | Karla, Annie | Due to the SD purchase, all timelines and product development schedules have been re-arranged. Linked cards by end of 2026, they hope
Piloting New BC Acquisition software | On Hold | Crystal, Annie | SD has paused development on BC Acq to focus on BC Circ. We are waiting on one, very small, bug fix so that Crystal can streamline the invoicing procedures that might still happen soon.
Improve volume handling in catalog and WF | On hold | Karla, Annie | Got shoved aside by Problem Items and other things.
Website development and support
Winnefox Extranet and Website | In Process | Jay | Rebuilding the Winnefox Extranet and folding the public facing website into it.
Upgrade Drupal 9 sites to Drupal 10 Upgrade remainging Winnefox websites | In Process | Jay | Drupal 9 sites need to be updated to Drupal 10. Like the upgrade from 8 to 9, the switch from 9 to 10 is a major version update and brings with it some significant user interface changes. Update 2/27/26: Sites affected (Winnefox, Princeton, Omro, Oxford, and Endeavor) will be replaced in 2027.
Accessibility for websites | In Process | Jay | Oshkosh needs to be compliant by April 2026, all other librariies April 2027, this also impacts Winnefox services such as the catalog.
Digitization/Indexing
"Bagging" & Uploading backup of ResCarta data to the state | In Process | Keetra | Participating in the statewide Digital Achive Backup project because it never hurts to have multiple backups!
Creating a ResCarta inventory | Near Done | Keetra | This was moved up the priority list because of our participation in the statewide Digital Archive Backup project.
Mitigate all possible ResCarta security concerns | In Process, ongoing | Keetra, Pete | Currently working on spinning up a replacement for the server with newer versions of the software.
Add Fond du Lac images to ResCarta | In Process | Keetra | Restructured directory of images to prepare for import.
Add Westfield yearbooks to ResCarta | In Process | Keetra
Add Berlin newspapers to ResCarta. | Upcoming | Keetra | Berlin is reviewing images received from Crowley.
Investigate interest in combined Cemetery index similar to Vital Records index | On Hold | Keetra | An email was sent out to directors inquiring whether their library had any paper or electronic records. Few libraries replied.
Investigate adding Wild Rose local history audio files to ResCarta | Upcoming | Keetra | This will be the first audio to be added.
Investigating collaboration with other library ResCarta sites in Wisconsin | Upcoming | Keetra
Other
Cleanup Overdrive Marketplace Accounts / Overdrive Support email configuration | Near Done | Keetra, Pete | Many accounts were out of date due to staff turnover, a number of email addresses were defunct. Waiting to hear back from a handful of libraries.